## ListOfFeatures
Product Backlog - Project Title (List of your features)
User Stories / List of features
User
Can sign up and log in into the system
Can buy a membership and cancel it anytime
Universal header and footer
When the person is logged in, he/she can enter his/her page and see basic informations
If he/she buy a pass with a promo code it's cheaper
Every button on site is active and working
Administartor
Can operate the databases without any issues

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
User Story/ Feature #1
Task : Make a universal header |  | Dawid | Done
Task : Make a universal footer |  | Dawid | Done
Task : Draw a database design |  | Dawid, Denis | Done
Taks: Discuss about features |  | Everybody | Done
Task : Create a database schema |  | Dawid, Denis | Done
User Story #2
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
MEMBERSHIP PAYMENT SITE |  | Dawid
Task Design page |  | Dawid,Denis | Done
Task Create |  | Dawid | Done
Task Make a JS animation |  | Dawid | Done
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
MEMBERSHIP PAYMENT SITE |  | Dawid
Task Make a payment form |  | Dawid | Done
Task form restrictions |  | Dawid | Done
Task Attach database |  | Dawid | Ongoing
Task Promo code implementation |  | Dawid | Ongoing
User Story #2
USER REGISTRATION SYSTEM |  | Denis
Task Attach database |  | Denis | Done
Task Login/SignUp page |  | Denis | Done
Task Personal profile page |  | Denis | Ongoing
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.